## PCC
Task | Sub-task | Owner | Priority | Due Date | Dependencies
Manage CPs/Spend a year focusing on maintenance | Follow CP process/keep up to date on process Clearly document voting, decisions, etc | CP Manager
| Clean up list of CPs -- did any get lost? | CP Manager
| Maintain list of active CPs (google spreadsheet) | CP Manager
| Follow up with CP owners | CP Manager
| Facilitate CP discussions, publish agendas, minutes | CP Manager
| Manage CP voting | CP Manager
| Schedule and facilitate CP calls | CP Manager
| Own CPs, update them, identify to CP manager that a CP is ready to be discussed | PCC participants
| Apply changes immediately to not lose track of agreement | TBD
| Update wiki PCC CP Process page item 3 to point to googledoc instead of listing CPs | TBD
Manage processes/Ensure we are following them, document decisions and voting |  | Amit Popat
Facilitate working calls | List profiles here… pick a lead cochair for each profile | TBD
Volume editing | Volume 1 | TBD
| Volume 2 | TBD
| Volume 3 | TBD
| Volume 4 | TBD
| TIs… (TBD | TBD
Deal with GAO (HL7 is getting rid of it)
Keep wiki updated | List of F2F meeting | Emma
| List of teleconferences for workitems | profile editors
| Main page of PCC profiles update/cleanup | TBD
Schedule tcons |  | Profile editors, Jeremiah
Focus on engagement | Manage Engagement process/Coordinate with marketing/comm | Thom Kuhn
| Manage list of profiles that need webinars | TBD
| Create content for profile webinars | TBD
| Deliver profile webinars | TBD
| Disseminate profile webinar recordings | TBD
| Recruit participants | TBD
| Identify avenues for outreach: conferences, associations, newsletters, mailing lists, blogs | TBD
| Identify content for dissemination | TBD
| Develop content | TBD
| Clean up WIKI | TBD
Develop a Welcome Letter (to send to new members)

## Cochairs
Task | Sub-task | Owner | Due Date | Dependencies
Manage publication process | Keep track of what Mary needs | Denise
| Fill out Mary's spreadsheet | Denise/Emma/Gila
| Guesstimate initial list based on current CPs + past TI repub stats | Emma, Denise, Gila, Steve | Next cochair meeting (Oct 6) | Denise will email Steve to beg him to join our Oct 6 call
Update Mary when new CPs come in/list changes
| Review Mary's documents before they go out | Editor + Emma, Denise, Gila, Amit
Kick off development cycle | Make sure editors have the right template to start with for proposal, supplement writing, etc | Emma |  | Beginning of the development year after Nov meeting
| Create a wiki page for new editors to post profile development details, meeting notes, etc | Emma |  | Beginning of the development year after Nov meeting
| Show new editors how to use FTP site, where to put stuff | Emma |  | Beginning of the development year after Nov meeting
| Prompt new editors to have calls and work with Jeremiah to schedule them using the HIMSS webex | Emma |  | Beginning of the development year after Nov meeting
Facilitate in-person meetings | Manage discussions to stay on agenda | Denise
| Take and post meeting notes | Emma, Gila and Denise to pool it, but Gila to consolidate and post notes |  |  | Denise can do the admit stuff, who was present, etc.
Set agendas | October | Emma |  |  | Emma would email people 2 weeks before the meeting to find out if they are participating via webex and what time zone they are in and ask if they plan to participate all the days or just some days
| November | Emma
| February (Volume 1) | Emma
| May (Public Comment) | Emma
| July (TI Publication) | Emma
Manage proposal review process | Manage incoming profiles | Emma and Amit
| Manage profile review tcons | Emma and Amit
| Facilitate October meeting | Emma and Amit
| Provide input as to technical capacity of TC | Emma and Amit
| Facilitate November meeting | Emma and Amit
PCC librarian | Manage PCC OIDs | Denise
| Manage FT section numbers | Denise
| PCC library cleanup | TBD, Emma, Gila and Denise to discuss