## Rating
# | Gap | Lead/Liason to other domain (only 1) responsible for delivering as appropriate for each gap. CPs: Write CP, present and discuss Profile: Write proposal and present, discuss w/committee; domain will determine profile author Public Comment: Write public comment and submit, discuss w/committee. | Co-Lead (maybe 1) assists Lead as needed; be willing to step up into lead position if needed | Mentors (at least 1) has previous experience in the IHE process and can provide guidance | Reviewers (at least 2) review providing constructive feedback; ideally has some experience in subject matter but is not required | Notes/Actions | Domain(s) | Status | Profile or CP? | Market Impact 5 All areas 4 Several 3 Some 2 Few 1 little/none | Global Benefit 5 6+ countries 4 4-5 countries 3 3-4 countries 2 2 countries 1 1 country | Effort (to write CP/Profile) 5 100+ pages 4 75-100 pages 3 50-75 pages 2 25-50 pages 1 <25 pages | Effort-Adjusted Higher score on effort negatively affects priority - this adjusts for that | Urgency in relation to profile depencies; 5 NOW! 4 soon 3 next cycle 2 after next cycle 1 whenever | Total | Average
7 | No RESTful/FHIR in PCC The base standard (FHIR) supports RESTful queries, but has not yet been profiled in IHE PCC. This is on PCC’s roadmap for future years. It was not considered for submission in the 2014/2015 development cycle due to the fact that FHIR had not yet reached DSTU status. | Keith/Dragon |  | n/a | Laura, Tone | - many different FHIR (RESTful) based initiatives across, S&I, Commonwell, HL7, etc. - pre-coordinate harmonization efforts Global Benefit: - EU projects, Canadian projects, Australia, Saudi - July F2F topic - ITI is doing FHIR for PDQ, for MHD, maybe restful ATNA - Keith has ideas to implement FHIR in QED update: 7/7/2014 - working on a proposal submitted, august/september timeline - no immediate action needed before F2F update: 7/21/2014 - QED updates will include mostly changes to Volume 2, describing how to use FHIR transactions. - will leave existing SOAP based QED transactions in place. - this is not a new profile, but will effectively be written as one. - current implementation/adoption: Orion, ICW, others.. | PCC/ITI/QRPH | Open | Profile | 5 | 4 | 3 | 3 | 4 | 16 | 4
3 | No population level queries in MHD The IHE Mobile Access to Health Documents (MHD) Profile does not support population level queries; however, the base standards do support this. This could be submitted as a new profile to Quality, Research and Public Health Domain. use case: MPQ in Public Health | Daniel Berezeanu | Dragon | Tone | Tone, Laura | - (per Gila) MHD is already in TI, so this must be a CP - John Moerkhe is lead on MHD in ITI update 7/7/2014: - no update at this time update 7/21/2014: - expect more of an update later in the week after ITI has their discussions update 7/22/2104: (QRPH joint meeting) - possible interest by QRPH will review an follow up with ITI if interest exists - no further action planned from PCC | ITI/QRPH | Closed - Passed to QRPH | CP | 4 | 2 | 2 | 4 | 5 | 15 | 3.75
5 | No pub/sub in MHD As written, the IHE Mobile Access to Health Documents profile does not presently support a publish/subscribe model, however this capability is supported by the base standards and could be incorporated as a change proposal or new profile submission. use case: DSUB use case(s) | ?? 6/23/14 - need to identify lead | Daniel Berezeanu | Keith | Tone, Laura | Market Impact: - MHD is still new - action: Keith to reach out to Josh Mandel for lead on this one update 7/7/2014: - Keith spoke with Josh - Josh will join ITI meeting at F2F when MHD is discussed - John Moerkhe welcomes assistance due to other MHD work update 7/21/2014: - FHIR has pub/sub via ATOM feed - expect more of an update later in the week after ITI has their discussions update 7/23/2014: (Joint w/ITI) - no need for any action here as this can be handled via FHIR+Atom Feed | ITI | Closed | CP | 3 | 2 | 2 | 4 | 5 | 14 | 3.5
4 | Extend DSUB to support MPQ queries This requirement could be met by extending the IHE Document Subscription (DSUB) profile to support the queries specified in the IHE Multipatient Query (MPQ) profile. This might be added as a change proposal or a new profile submission to IHE IT Infrastructure. use case: MPQ+DSUB; EHR subscribes to updates to results that link to a reportable event (supports quality measurement). | ?? 6/23/14 - need to identify lead |  | Keith | Tone | - Write CP - action: Tone to solicit someone in QRPH update 7/7/2014: - Tone reached out, no response yet, will follow up update 7/21/2014: - no committment on lead yet, will follow up while at F2F. Update 7/22/2014: (QRPH joint) - possible interest by QRPH will review an follow up with ITI if interest exists - no further action planned from PCC | QRPH/ITI | Closed - Passed to QRPH | CP | 4 | 2 | 2 | 4 | 3 | 13 | 3.25
6 | No population level queries in QED The IHE QED profile does not support population level queries. A simple extension to this profile could be made to allow for matching without a patient identifier being specified, or a new profile submission could be made. | Keith | Dan Chaput | n/a | Tone | - relates to Gaps 1 and 2 - QED adoption is low, Gaps 1 and 2 may be based on FHIR, resulting in quicker adoption - base level functionality - needs to be in place before PCC moves to RESTful approaches - Write CP to QED to add an option for MPQ update 7/7/2014: - CP will be written/submitted prior to F2F update 7/21/2014: - Keith to write CP to review at F2F - currently the profile requires a single patientId, need to rewrite to accept a null flavor/value instead, changing the behavior of the transaction | PCC | Open | CP | 3 | 2 | 1 | 5 | 3 | 13 | 3.25
1 & 2 | Unrestricted patient demographics queries (1) IHE ITI has not developed profiles to support unrestricted queries for patients matching demographics criteria. Most information systems in a healthcare environment have access to an organizational MPI. This could be a profile submission to the Quality, Research and Public Health Domain. We note that most user stories for queries based on patient demographics also inquire about patients with a particular disease, or presence or absence of diagnostic test. Pub/Sub for patient demographics (2) IHE ITI has not published a profile supporting a publish/subscribe model for accessing patient demographics data. This could be a profile submission to the ITI Technical Committee. | ?? 6/23/14 - need to identify lead |  |  |  | - impacts Quality, research and public health - proposal needs to include appropriate sec. constraints - possibly relates to "Joel's one step query" - New profile proposal to QRPH (use cases are QRPH centric) Global Benefit: - India initiatives - Saudi - action: solicit feedback from non-US community on all Gaps Effort: - build of PDQM (for mobile) - slightly higher b/c pub/sub adds comlexity action: Tone to reach out to QRPH update 7/7/2014: - Tone to follow up with QRPH update 7/21/2014: - Tone to get this on joint meeting agenda update 7/22/2014:(Joint w/QRPH) - could possibly be addressed by QUICK (HL7 initiative referenced by S&I) - discussed Research Matching Protocol (RM), not a viable option - discussed QME-EH profile, not a viable option - no further action planned from PCC | QRPH/ITI | Closed - Passed to QRPH | Profile | 4 | 2 | 3 | 3 | 3 | 12 | 3
8 & 9 | Care Record DSTU version referenced in QED (8) and CM (9) The IHE QED profile needs to be updated to support the HL7 Version 3 Care Record Standard that is now normative. The current content relies on the HL7 Version 3 DSTU. The IHE CM profile should be updated to support the HL7 Version 3 Care Record Standard, and should also take advantage of HQMF Release 2, which supports identification of data elements that are needed in support of patient care (the HQMF data element model was informed by this profile). | ?? 6/23/14 - need to identify lead |  |  |  | - merge 8 and 9 - Could be either Profile or CP (need committee consideration) QED to support normative version of Care Record Global Benefit: - QED implemented in 3 or 4 countries - given FHIR based work takes priority in this list, QED and CM may have continued challenges getting uptake on SOAP approach. Can revisit next cycle-i.e. profile proposals being accepted in calendar year 2015(per urgency prioritization score). Update 7/7/2014: - no need to collect ongoing updates until next cycle | PCC | Deferred | Either | 2 | 3 | 3 | 3 | 2 | 10 | 2.5
10 & 11 | No query (10) or subscription (11) model has been developed for SMTP w/in XDM profile The IHE XDM profile could be used with an SMTP protocol as an alternative mechanism to respond to query requests reusing existing IHE transactions. No query model has been developed for SMTP to send a query request The IHE XDM profile could be used with an SMTP protocol as an alternative mechanism to send notifications. No subscription model has been developed for SMTP. | Joel Ryba | Dan Chaput | Tone |  | - includes gaps 10 and 11 - should be able to reuse metadata from existing profiles, work will be in defining how the underlying protocol works - Add an SMTP based response mechanism (e.g. notification) to XDM - Joel Ryba is working on similar initiatives in S&I Update 7/7/2014: - Dan to follow up with Joel update 7/21/2014: - S&I group (Joel is leading) is working on SMTP+XD metadata query and combined query/retrieve. not sure where subscription matches up to those S&I efforts. update 7/23/2014: (Joint w/ITI) - general feeling of ITI is that this would not get approved: - other mechanisms exist (XDS,XCA) - security concerns - sql injection, etc. - no further action planned from PCC | ITI | Closed - If further action is desired then the lead (or someone) will need to approach ITI via a CP or new profile proposal | Profile | 3 | 1 | 3 | 3 | 3 | 10 | 2.5
[7 empty] | ITI |  | Profile | 3 | 1 | 3 | 3 | 3 | 10 | 2.5

## National Initiatives
Gap | Proposed Resolution | List national or regional programs and initiatives below that would be impacted by these gaps being addressed
1 | IHE ITI has not developed profiles to support unrestricted queries for patients matching demographics criteria. Most information systems in a healthcare environment have access to an organizational MPI. This could be a profile submission to the Quality, Research and Public Health Domain. We note that most user stories for queries based on patient demographics also inquire about patients with a particular disease, or presence or absence of diagnostic test. | India, Saudi
2 | IHE ITI has not published a profile supporting a publish/subscribe model for accessing patient demographics data. This could be a profile submission to the ITI Technical Committee. | India, Saudi
3 | The IHE Mobile Access to Health Documents (MHD) Profile does not support population level queries; however, the base standards do support this. This could be submitted as a new profile to Quality, Research and Public Health Domain.
4 | This requirement could be met by extending the IHE Document Subscription (DSUB) profile to support the queries specified in the IHE Multipatient Query (MPQ) profile. This might be added as a change proposal or a new profile submission to IHE IT Infrastructure.
5 | As written, the IHE Mobile Access to Health Documents profile does not presently support a publish/subscribe model, however this capability is supported by the base standards and could be incorporated as a change proposal or new profile submission to the Quality, Research and Public Health Domain.
6 | The IHE QED profile does not support population level queries. A simple extension to this profile could be made to allow for matching without a patient identifier being specified, or a new profile submission could be made.
7 | The base standard (FHIR) supports RESTful queries, but has not yet been profiled in IHE PCC. This is on PCC’s roadmap for future years. It was not considered for submission in the 2014/2015 development cycle due to the fact that FHIR had not yet reached DSTU status. | EU projects, Canadian projects, Australia, Saudi
8 | The IHE QED profile needs to be updated to support the HL7 Version 3 Care Record Standard that is now normative. The current content relies on the HL7 Version 3 DSTU.
9 | The IHE CM profile should be updated to support the HL7 Version 3 Care Record Standard, and should also take advantage of HQMF Release 2, which supports identification of data elements that are needed in support of patient care (the HQMF data element model was informed by this profile).
10 | The IHE XDM profile could be used with an SMTP protocol as an alternative mechanism to respond to query requests reusing existing IHE transactions. No query model has been developed for SMTP to send a query request..
11 | The IHE XDM profile could be used with an SMTP protocol as an alternative mechanism to send notifications. No subscription model has been developed for SMTP.